## Extraction 1.0
Version | Start Date | End Date | Comments
Titanic 1.0.0 | 2024 07 28 | 2024 07 29 | Began EDA
Titanic 1.0.1 | 2024 07 29 | 2024 07 30 | Feature Extraction, PassengerId, Name, Cabin
Titanic 1.0.2 | 2024 07 30 | 2024 07 30 | Feature Extraction, Total Speinding, Solo Traveler
Titanic 1.0.2 | 2024 08 07 | 2024 08 07 | Feature Extraction: AgeGroup, FamilySize. Saved feature engineered datasets as train and test.
I need to impute missing data before some accumulated data: AgeGroup, FamilySize, Spent
I need to impute missing data first. I will redo this file.

## EDA 2.0
Version | Start Date | End Date | Comments
Titanic 2.0.0 | 2024 07 30 | 2024 07 30 | EDA Started.
Titanic 2.0.1 | 2024 08 01 | 2024 08 01 | Experiment with Pie Charts
Titanic 2.0.3 | 2024 08 01 | 2024 08 01 | Experiment with Pie Charts looks good. I will go with it.
Titanic 2.0.4 | 2024 08 02 | 2024 08 02 | Continue EDA. Decided to do both Transport True and Transport False in Pie Charts
Titanic 2.0.5 | 2024 08 05 | 2024 08 05 | Completed pie charts on Lone, Spent, VIP, CryoSleep
Titanic 2.0.6 | 2024 08 07 | 2024 08 07 | Moved to Titanic 3.0.0. to deal with missing values using Titanic 1.0.2
Titanic EDA 2.0.1 | 2024 08 27 | 2024 08 27 | Titanic EDA 2.0.1 Modified
DONE
Titanic EDA 2.0.2 | 2024 08 28 | 2024 08 28 | Adding insights.

## Missing 3.0
Version | Start Date | End Date | Comments
Titanic 3.0.0 | 2024 08 07 | 2024 08 07 | Created from Titanic 1.0.2
Stopped at Imputing Home Planet Missing Values.
Name Extraction, Age Group, and family size are here.
Titanic 3.0.1 | 2024 08 08 | 2024 08 08 | Deleted Age Group, Family size to deal with missing values
HomePlanet Missing Values
Done
Titanic 3.0.2 | 2024 08 08 | 2024 08 09 | CryoSleept Missing Values (Strarting with 3.0.0)
Imputed Missing values with False since most passengers were False.
Done
Titanic 3.0.3 | 2024 08 09 | 2024 08 09 | Destination Planet. Start with Titanic 3.0.1 and use the same method as for HomePlanet.
Done
Titanic 3.0.4 | 2024 08 09 | 2024 08 09 | Cabin Deck Imputation (Starting with Titanic 3.0.1). The imputation will be based on HomePlanets. This file contains HomePlanet imputation.
** Since we are filling CabinDeck and HomePlanet by LastName, we should Impute this first. **
** We should also imputer missing values for luxury spending with 0**
Titanic 3.0.5 | 2024 08 09 | 2024 08 09 | LastName Missing Values (Strarting with 3.0.0)
Done
Titanic 3.0.6 | 2024 08 12 | 2024 08 12 | Make Missing values of Luxury Godds = 0 (Strarting with 3.0.0)
Done
Titanic 3.0.7 | 2024 08 12 | 2024 08 12 | Cabin Side Missing Values (Strarting with 3.0.0)
Done
Titanic 3.0.8 | 2024 08 13 | 2024 08 13 | Cabin Number Missing Values (Start with 3.0.0)
Titanic 3.0.8 | 2024 08 13 | 2024 08 13 | A black line appears underneath the scatter plot. I couldn't figure out why.
Done
Titanic 3.0.10 | 2024 08 13 | 2024 08 13 | Cabin Side Missing Values (Start 3.0.0)
Done
Titanic 3.0.11 | 2024 08 13 | 2024 08 14 | Age (Start with 3.0.0)
Done

## Overview 4.0
Version | Start Date | End Date | Data Overview
Titanic 4.0.0 | 2024 08 14 | 2024 08 14 | Data Overview (Start Titanic 1.0.2)
Done

## Preprocess 5.0
Version | Start Date | End Date | Data Overview
Titanic 5.0.0 | 2024 08 16 | 2024 08 16 | Preprocessing (Start Titanic 1.0.2)
Saved file data as data in the Data Folder.
Done
Titanic 5.0.1 | 2024 08 18 | 2024 08 18 | Imputed Age by Median so Age Group can be determined.
Done
Titaninc 5.0.2 | 2024 08 19 | 2024 08 19 | Concatenated Train and Test Data in a different way.
Done
Notes
Add heatmap

## Missing 6.0
Version | Start Date | End Date | Data Overview
Titanic 6.0.0 | 2024 08 16 | 2024 08 16 | Start Titanic 3.0.1 Home Planet
Done
Start Titanic 3.0.3 Destination
Done
Start Titanic 3.0.4 Cabin Deck
Done
Titanic 6.0.1 | 2024 08 18 | 2024 08 18 | Start Titanic 3.0.7 Cabin Side
Done
Start Titanic 3.0.8 Cabin Number
Done
Titanic 6.0.2 | 2024 08 18 | 2024 08 18 | Cryosleep
Done
VIP
Done

## ML 7.0
Version | Start Date | End Date | Data Overview
Titanic 7.0.0 | 2024 08 18 | 2024 08 20 | Start Titanic 6.0.2
Start ML: Logistic Regression and others
Titanic 7.0.1 | 2024 08 21 | 2024 08 21 | CAT BOOST doesn't work.
Started newevn virtual environment.
Titanic 7.0.2 | 2024 08 22 | 2024 08 22 | Started FRESH spaceenv to test issue with CAT Boost
Use Windows Command in Administrative Mode.
DONE
Titanic 7.0.3 | 2024 08 22 | 2024 08 22 | Grid Search Began
XGBoost, LIGHTGBM and CATboost show the best results (over 80%)
Titanic 7.0.5 | 2024 08 26 | 2024 08 26 | Final checks.

## Project
Version | Start Date | End Date | Data Overview
Consider other types of encoders: Target, WOEEncoder
Stratifed Split
F1-score or PR AUC
Repeated Code
Other types of scaling
black formatter: Long lines
PEP 8
PyLint
Collinearity

## Pipelines
Version | Start Date | End Date | Comments

## Ideas
Number | Topic | Idea
AUC and ROC
1 | AUC | AUC is more robust than precision and recall
| ROC Curve | Wine Project
Thresholds
3 | Yellow Brick | Threshold plot for threshold of precision and recall
Correlations
4 | Feature Correlation | Eliminate collinearity
Explainability
5 | SHAP | Insurance project
6 | LIME
Feature Engine Library
7 | Feature Engine Library | Excellent Library for many things
Hyperparameter Optimization
| Optuna | Hyperparameter optimizaton (Insurance project)
Imbalanced Data
| Balance | Balance the data not by adding or taking away data but by weights.
| K-Fold on mulitple models | Insurance project
| Outliers | Create a new column that shows which row is an outlier (1) and which is not (0)
Outliers in Football Project
Outliers in Coursera Project
| Scaling | Wine Project
| Models | It’s important to use the right model for the right type of problem: Regression or Classification
According to Pertu, models that get the best performance are XGB Boost and LITE GPM
| Bar Plots | Stroke Project
Side by Side Bar Plots
Pie Chart
| Single Pie Chart | COVID
| Multiple Pie Charts in one Line | Mental Health
| Windows Prompt | Use it in administrative mode to add librarires.